## Sheet1
Project_Number | Project_Name | Section | Funding_Program | Project_Start_Yr | Project_End_Yr | SqYdsRampsEstimate | SqYdsRampsActual | NumRampsEstimate | NumRampsActual
PW12360-001 | West Jefferson Blvd curbface walk | Transportation Engineering - Curbs and Sidewalk | N - Not Funded by Public Works | 2014 | 2014 | 30 | 32 | 2 | 3
PW12363-001 | N. Clinton Str./Fairington Dr. intersection improvements | Transportation Engineering - Intersection Improvement | C - Concrete Streets (CONC) | 2014 | 2014 | 36 | 16 | 4 | 4
PW12376-001 | Brookshire Circle Concrete Street Reconstruction | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2014 | 2014 | 83 | 70 | 8 | 11
PW12372-001 | Lake Pointe Villas Concrete Street Repairs | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2014 | 2014 | 50 | 55 | 6 | 6
PW12375-001 | Fourth Street Brick Replacement | Transportation Engineering - Other (specify in Scope) | B - Brick Streets (BRCK) | 2014 | 2014 | 0 | 0 | 7 | 7
PW12379-001 | Crown Colony Addition concrete street Improvements | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2014 | 2014 | 800 | 586 | 70 | 68
PW12373-001 | Southwick Village Concrete Street Repairs | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2014 | 2014 | 242 | 192 | 18 | 18
PW12384-001 | Haverhill Area Concrete Street Repairs | Transportation Engineering - Concrete Street Repair - Neighborhood Street | C - Concrete Streets (CONC) | 2014 | 2015 | 438 | 474 | 124 | 98
PW12374-001 | Butler Street Brick Street Replacement | Transportation Engineering - Other (specify in Scope) | B - Brick Streets (BRCK) | 2014 | 2014 | 55 | 58 | 16 | 16
PW12361-001 | Park Avenue sidewalk improvement | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2014 | 2014 | 15 | 17 | 2 | 2
PW12359-001 | Sandpiper Cove Concrete Street Reconstruction | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2014 | 2014 | 97 | 80 | 11 | 11
PW12383-001 | Crestwood Colony Area Concrete Street Repairs | Transportation Engineering - Concrete Street Repair - Neighborhood Street | C - Concrete Streets (CONC) | 2014 | 2015 | 244 | 233 | 145 | 135
PW12344-001 | Oxford Street Concrete Repair/Road Diet | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2014 | 2015 | 448 | 443 | 34 | 34
PW12380-001 | Hillcrest Asphalt Street Repairs | Transportation Engineering - Asphalt Street Reconstruction | A - Asphalt Streets (RESF) | 2015 | 2016 | 256 | 230 | 33 | 31
PW0069A-000 | Jefferson Boulevard Road Diet | Transportation Engineering - Asphalt Street Reconstruction | A - Asphalt Streets (RESF) | 2015 | 2015 | 303 | 405 | 49 | 49
PW12329-001 | St. Joe Center Road sidewalk connection (south side) | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2015 | 2015 | 16 | 19 | 2 | 2
PW0055S-000 | Runnion Avenue Sidewalk Improvements | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2015 | 2015 | 120 | 121 | 14 | 14
PW0022C-000 | Tower Heights/Hamilton Association/North Highlands/Lincoln Park Concrete Street Repairs | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2015 | 2016 | 2720 | 2443 | 662 | 606
PW0064S-000 | Maiden Lane Sidewalk Improvement | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2015 | 2015 | 45 | 41 | 3 | 3
PW0056C-000 | Winterset Addition Concrete Street Repairs | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2015 | 2015 | 80 | 32 | 18 | 18
PW0006S-000 | Cook Road Sidewalk Improvement | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2015 | 2015 | 12 | 20 | 2 | 3
PW0018C-000 | McKinnie Avenue Concrete Street Repairs/Road Diet | Transportation Engineering - Concrete Street Reconstruction - Arterial | C - Concrete Streets (CONC) | 2015 | 2016 | 420 | 251 | 34 | 34
PW0025C-000 | Hoevelwood Civic/Hickory Grove/Casselwood Concrete Street Repairs | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2015 | 2016 | 580 | 558 | 85 | 76
PW0049C-000 | Eagle Creek Concrete Street Repairs | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2016 | 2016 | 177 | 131 | 28 | 24
PW0052A-000 | Spy Run Avenue and Livingston Avenue Intersection Improvement | Transportation Engineering - Intersection Improvement | A - Asphalt Streets (RESF) | 2016 | 2016 | 14 | 14 | 2 | 2
PW12382-001 | Arlington Park Area Concrete Street Repairs Phase 1 | Transportation Engineering - Concrete Street Repair - Neighborhood Street | C - Concrete Streets (CONC) | 2016 | 2017 | 117 | 117 | 24 | 24
PW0032C-000 | Eagle Lake Concrete Street Repairs | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2016 | 2016 | 284 | 320 | 28 | 29
PW0005A-000 | Maumee Avenue Realignment - Harmar Street to University Street | Transportation Engineering - Asphalt Street Reconstruction | A - Asphalt Streets (RESF) | 2016 | 2016 | 120 | 118 | 18 | 17
PW0061S-000 | Reed Road Sidewalk Improvements | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2016 | 2016 | 18 | 19 | 4 | 4
PW0124S-000 | Jefferson Blvd and Lafayette St Northeast Corner Improvement | Transportation Engineering - Curbs and Sidewalk | S - Sidewalks (PEDS) | 2016 | 2016 | 19 | 19 | 2 | 2
PW0115N-000 | Pedestrian Safety Sidewalk Improvements for Clinton Street | Transportation Engineering - Curbs and Sidewalk | N - Not Funded by Public Works | 2016 | 2016 | 16 | 17 | 2 | 2
PW0160S-000 | South Hanna Street Sidewalk Connection | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2016 | 2016 | 30 | 24 | 5 | 7
PW0175S-000 | 5910 Hessen Cassel Road Sidewalk Construction | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2016 | 2017 | 10 | 7 | 1 | 2
PW0019C-000 | Pine Valley/Windrift Concrete Street Repairs | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2017 | 2017 | 500 | 574 | 66 | 76
PW0119C-000 | Arlington Park, Phase 2, Area Concrete Street Repairs | Transportation Engineering - Concrete Street Repair - Neighborhood Street | C - Concrete Streets (CONC) | 2017 | 2017 | 228 | 315 | 38 | 61
PW0174S-000 | Fairfield Avenue Sidewalk Repairs | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2017 | 2017 | 35 | 47 | 4 | 5
PW0062C-000 | Coldwater Road Rehabilitation | Transportation Engineering - Concrete Street Reconstruction - Arterial | C - Concrete Streets (CONC) | 2017 | 2017 | 191 | 351 | 32 | 33
PW0158C-000 | Memorial Way Concrete Street Reconstruction | Transportation Engineering - Concrete Street Reconstruction - Arterial | C - Concrete Streets (CONC) | 2017 | 2017 | 22 | 12 | 2 | 2
PW12442-001 | Hobson Road Concrete Street Improvements | Transportation Engineering - Concrete Street Reconstruction - Arterial | C - Concrete Streets (CONC) | 2017 | 2017 | 176 | 217 | 26 | 26
PW0166S-000 | Study Elementary sidewalk extension | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2017 | 2017 | 15 | 12 | 3 | 3
PW0059S-000 | Steup Avenue Improvements | Transportation Engineering - Other (specify in Scope) | S - Sidewalks (PEDS) | 2017 | 2017 | 364 | 256 | 36 | 36
PW0142C-000 | Pointe Inverness Way Concrete Street Reconstruction | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2017 | 2017 | 60 | 29 | 4 | 4
PW0223S-000 | 4800 Old Mill Road Sidewalk Improvement | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2017 | 2017 | 0 | 15 | 6 | 5
PW0154A-000 | Getz Road/Constitution Drive Intersection Improvements | Transportation Engineering - Intersection Improvement | A - Asphalt Streets (RESF) | 2017 | 2017 | 60 | 45 | 4 | 4
PW12417-001 | Maysville Road Widening - Stellhorn Road to Meijer Drive | Transportation Engineering - Road Widening | N - Not Funded by Public Works | 2017 | 2019 | 254 | 315 | 35 | 19
PW0198S-000 | 4001-4011 South Wayne Ave. Curb & Sidewalk improvements | Transportation Engineering - Curbs and Sidewalk | S - Sidewalks (PEDS) | 2017 | 2017 | 15 | 11 | 2 | 2
PW0239S-000 | Bluffton Road Sidewalk Construction | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2017 | 2017 | 11 | 11 | 2 | 2
PW12030-001 | State Blvd Realignment - Cass Street to Spy Run | Transportation Engineering - Road Widening | F - Federal Matching Dollars (FEDS) | 2018 | 2020 | 178 | 182 | 10 | 10
PW12227-001 | Dupont Rd Added Travel Lanes Project | Transportation Engineering - Road Widening | F - Federal Matching Dollars (FEDS) | 2018 | 2019 | 762 | 591 | 61 | 61
PW0120C-000 | Pine Valley Addition , Phase 2, Concrete Street Repairs | Transportation Engineering - Concrete Street Repair - Neighborhood Street | C - Concrete Streets (CONC) | 2018 | 2019 | 330 | 330 | 22 | 22
PW0015C-000 | Lima Valley Association Concrete Street Repairs | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2018 | 2018 | 25 | 34 | 6 | 7
PW0265C-000 | Old Auburn Cove concrete street reconstruction | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2018 | 2018 | 11 | 12 | 2 | 2
PW0143C-000 | North Anthony Blvd Rehabilitation | Transportation Engineering - Concrete Street Reconstruction - Arterial | C - Concrete Streets (CONC) | 2018 | 2018 | 168 | 179 | 13 | 13
PW0021C-000 | North Franke Park Street Rehabilitation | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2018 | 2018 | 25 | 15 | 4 | 4
PW0108W-000 | St. Joe Center Road Sidewalk: ±1350' East of Reed Road to Maplecrest Road | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2018 | 2018 | 7 | 8 | 1 | 1
PW0030C-000 | Greater McMillen Park Concrete Street Repairs, Phase 1 | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2018 | 2019 | 240 | 272 | 30 | 30
PW0232S-000 | Decatur Road Sidewalk Connection | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2018 | 2018 | 60 | 48 | 5 | 5
PW0256S-000 | Bluffton Road Sidewalk Construction, Phase 2 | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2018 | 2018 | 0 | 0 | 2 | 2
PW0231S-000 | North Clinton Street Sidewalk Connection | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2019 | 2019 | 98 | 93 | 14 | 14
PW0285P-000 | Columbia Street Streetscape | Transportation Engineering - Other (specify in Scope) | P - Special Projects (PJTS) | 2019 | 2020 | 15 | 11 | 3 | 2
PW0184N-000 | Ardmore Avenue Improvements - Aiport Expressway to Second Street | Transportation Engineering - Road Widening | N - Not Funded by Public Works | 2019 | 2020 | 200 | 105 | 10 | 8
PW0184N-000 | Ardmore Avenue Improvements - Aiport Expressway to Second Street | Transportation Engineering - Road Widening | N - Not Funded by Public Works | 2019 | 2020 | 200 | 105 | 10 | 8
PW0182S-000 | Reed Road Sidewalk Connection, Phase 1 | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2019 | 2019 | 55 | 47 | 9 | 9
PW0026C-000 | Caribe Colony Addition Concrete Street Repairs | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2019 | 2019 | 56 | 111 | 8 | 15
PW0020C-000 | Hillsboro Concrete Street Repairs | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2019 | 2019 | 600 | 500 | 54 | 55
PW0338C-000 | Greater McMillen Park Concrete Street Repairs, Phase 2 | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2019 | 2019 | 90 | 65 | 10 | 10
PW0397R-000 | Harrison Street Urban Trail | Transportation Engineering - Trail | R - Trails (RVGW) | 2019 | 2020 | 80 | 80 | 3 | 4
PW0173S-000 | St. Joe Center Rd Sidewalk Connection, Phase 1 | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2019 | 2019 | 98 | 131 | 12 | 19
PW0205C-000 | Aboite Meadows Concrete Street Repairs | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2019 | 2020 | 48 | 25 | 5 | 5
PW0036S-000 | Washington/Jefferson Blvd's @ Swinney Park Sidewalk Project, Phase 1 | Transportation Engineering - Curbs and Sidewalk | S - Sidewalks (PEDS) | 2019 | 2020 | 90 | 73 | 8 | 8
PW0034A-000 | Goshen Road Reconstruction | Transportation Engineering - Asphalt Street Reconstruction | A - Asphalt Streets (RESF) | 2019 | 2020 | 500 | 238 | 50 | 50
PW0385S-000 | Decatur Road Sidewalk Connection, Phase 2 | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2019 | 2019 | 12 | 7 | 2 | 2
PW0329C-000 | Oakmont Concrete Street Repairs | Transportation Engineering - Concrete Street Repair - Neighborhood Street | C - Concrete Streets (CONC) | 2019 | 2019 | 15 | 14 | 1 | 1
PW0354C-000 | Woodhurst Addition Concrete Street Repairs | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2019 | 2020 | 225 | 155 | 32 | 40
PW12269-001 | Maplecrest Road Widening - State Blvd to Stellhorn Road | Transportation Engineering - Road Widening | F - Federal Matching Dollars (FEDS) | 2019 | 2020 | 49 | 50 | 14 | 14
PW0342S-000 | East Washington Blvd Sidewalk Connection | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2019 | 2019 | 40 | 44 | 4 | 4
PW0413B-000 | Wilt Street: Brick Street Repair | Transportation Engineering - Brick Street | B - Brick Streets (BRCK) | 2019 | 2019 | 6 | 8 | 1 | 1
PW0311S-000 | Bluffton Road Sidewalk Construction, Phase 3 | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2019 | 2020 | 27 | 22 | 5 | 5
PW12269-001 | Maplecrest Road Widening - State Blvd to Stellhorn Road | Transportation Engineering - Road Widening | F - Federal Matching Dollars (FEDS) | 2019 | 2020 | 49 | 50 | 14 | 14
PW12269-001 | Maplecrest Road Widening - State Blvd to Stellhorn Road | Transportation Engineering - Road Widening | F - Federal Matching Dollars (FEDS) | 2019 | 2020 | 49 | 50 | 14 | 14
PW0034A-000 | Goshen Road Reconstruction | Transportation Engineering - Asphalt Street Reconstruction | A - Asphalt Streets (RESF) | 2019 | 2020 | 500 | 238 | 50 | 50
PW0034A-000 | Goshen Road Reconstruction | Transportation Engineering - Asphalt Street Reconstruction | A - Asphalt Streets (RESF) | 2019 | 2020 | 500 | 238 | 50 | 50
PW0307S-000 | Reed Road Sidewalk Connection, Phase 2 | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2020 | 2020 | 5 | 5 | 1 | 1
PW0180S-000 | Stellhorn Road Sidewalk Connection, Phase 1 | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2020 | 2020 | 60 | 62 | 7 | 7
PW0418C-000 | Tanbark Community Concrete Street Repairs | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2020 | 2020 | 304 | 212 | 36 | 42
PW0402C-000 | Traders Pointe concrete street repair | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2020 | 2020 | 30 | 33 | 3 | 3
PW0361N-000 | Summit Park Sidewalk, Phase 1B | Transportation Engineering - Sidewalk | N - Not Funded by Public Works | 2020 | 2021 | 20 | 13 | 2 | 2
PW0404C-000 | Greater McMillen Park Concrete Street Repairs Phase 3 | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2020 | 2020 | 70 | 50 | 10 | 10
PW0420C-000 | Aspen Village Concrete Street Repairs | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2020 | 2021 | 60 | 113 | 16 | 16
PW0440C-000 | Glenwood Park Concrete Street Repairs | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2020 | 2021 | 36 | 0 | 4 | 2
PW0437A-000 | Burns Blvd Street Improvements | Transportation Engineering - Asphalt Street Reconstruction | A - Asphalt Streets (RESF) | 2020 | 2021 | 50 | 48 | 14 | 14
PW0426S-000 | Clinton Street Lane Reduction | Transportation Engineering - Curbs and Sidewalk | S - Sidewalks (PEDS) | 2020 | 2020 | 50 | 39 | 3 | 3
PW0296S-000 | Bluffton Road Sidewalks, Phase 1 | Transportation Engineering - Sidewalk | S - Sidewalks (PEDS) | 2021 | 2021 | 80 | 65 | 12 | 12
PW0491C-000 | Brookside Park Concrete Street Repairs | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2021 | 2021 | 65 | 136 | 12 | 10
PW0498C-000 | Sherwood to Pettit Neighborhood Concrete Repairs | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2021 | 2021 | 119 | 119 | 16 | 16
PW0489C-000 | Springwood-Orchard Woods Concrete Street Repairs Phase II | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2021 | 2021 | 30 | 125 | 1 | 14
PW0458A-000 | Vance Avenue Street Repairs | Transportation Engineering - Asphalt Street Reconstruction | A - Asphalt Streets (RESF) | 2021 | 2021 | 25 | 32 | 3 | 6
PW0441C-000 | Greater McMillen Park Concrete Street Repairs, Phase IV | Transportation Engineering - Concrete Street Reconstruction - Neighborhood Street | C - Concrete Streets (CONC) | 2021 | 2021 | 15 | 19 | 3 | 3
PW0315C-000 | Pettit-Rudisill Neighborhood Concrete Street Repairs Phase 1 | Transportation Engineering - Concrete Street Repair - Neighborhood Street | C - Concrete Streets (CONC) | 2021 | 2022 | 90 | 90 | 10 | 10